## Sprint backlog
Sprint Log 1 - News API
Completed | User Story | Tasks
In Progress | As a user I want to read the article related to the song on the playlist | SCRUM | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Start Date | 2019-10-22 | Day of the Sprint | Target | Actual
Not Started |  | Sprint Chart | [7 empty] | Sprint End Date | 2019-10-29 | 0 | 5 | 5
|  | Pair Programming Logs | [7 empty] | Sprint Length (Days) | 7 | 1 | 4.2857 | 0
|  | Meeting Logs | [7 empty] | Sprint Points | 5 | 2 | 3.5714 | 0
|  | Artefact | [7 empty] | Expected Average Daily Sprint Points | 0.71429 | 3 | 2.8571 | 0
|  | Authorise News API key | [9 empty] | 4 | 2.1429 | 0
|  | Make web requests for news metadata | [7 empty] | Completion Time | 1 | 5 | 1.4286 | 0
|  | Parse through metadata to sort articles into title, author, description etc | [7 empty] | Average Daily Sprint Points Completed | 5 | 6 | 0.71429 | 0
|  | Testing | [9 empty] | 7 | 0 | 0
Test Get function
Test Load_Articles function
Sprint Log 2 - Create a GUI
| User Story | Tasks
| As a user I want a user friendly, easy and efficient GUI so that my experience is pleasant and enjoyable. | SCRUM | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Start Date | 2019-10-29 | Day of the Sprint | Target | Actual
|  | Sprint Chart | [7 empty] | Sprint End Date | 2019-11-05 | 0 | 5 | 5
|  | Pair Programming Logs | [7 empty] | Sprint Length (Days) | 7 | 1 | 4.2857 | 2.5
|  | Meeting Logs | [7 empty] | Sprint Points | 5 | 2 | 3.5714 | 0
|  | Artefact | [7 empty] | Expected Average Daily Sprint Points | 0.71429 | 3 | 2.8571 | 0
|  | Create a news panel to display articles | [9 empty] | 4 | 2.1429 | 0
|  | Create a song panel to display tracks | [7 empty] | Completion Time | 2 | 5 | 1.4286 | 0
|  | Create buttons to fetch articles/play songs etc | [7 empty] | Average Daily Sprint Points Completed | 2.5 | 6 | 0.71429 | 0
|  | Testing | [9 empty] | 7 | 0 | 0
Test panel displays data correctly
Test buttons work correctly
Sprint Log 3 - Query spotify results
| User Story | Tasks
| As a user I want to authorise my account without any errors so that I can access Spotify’s news related playlists. | SCRUM | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Start Date | 2019-11-05 | Day of the Sprint | Target | Actual
|  | Sprint Chart | [7 empty] | Sprint End Date | 2019-11-12 | 0 | 5 | 5
|  | Pair Programming Logs | [7 empty] | Sprint Length (Days) | 7 | 1 | 4.2857 | 2.5
|  | Meeting Logs | [7 empty] | Sprint Points | 5 | 2 | 3.5714 | 2.5
|  | Artefact | [7 empty] | Expected Average Daily Sprint Points | 0.71429 | 3 | 2.8571 | 0
|  | Authorise Spotify Client ID | [9 empty] | 4 | 2.1429 | 0
|  | Make song query on input string | [7 empty] | Completion Time | 2 | 5 | 1.4286 | 0
|  | Display song data based on query using song panel | [7 empty] | Average Daily Sprint Points Completed | 2.5 | 6 | 0.71429 | 0
|  | Testing | [9 empty] | 7 | 0 | 0
Test QueryList function
Test Load_Tracks function
Sprint Log 4 - Create a word extractor
| User Story | Tasks
| As a user I want to be able to download my news related playlist to listen offline | SCRUM | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Start Date | 2019-11-12 | Day of the Sprint | Target | Actual
|  | Sprint Chart | [7 empty] | Sprint End Date | 2019-11-19 | 0 | 5 | 5
|  | Pair Programming Logs | [7 empty] | Sprint Length (Days) | 7 | 1 | 4.2857 | 4
|  | Meeting Logs | [7 empty] | Sprint Points | 5 | 2 | 3.5714 | 3
|  | Artefact | [7 empty] | Expected Average Daily Sprint Points | 0.71429 | 3 | 2.8571 | 2
|  | Fetch titles of news articles | [9 empty] | 4 | 2.1429 | 2
|  | Take titles and extract key words/phrases | [7 empty] | Completion Time | 5 | 5 | 1.4286 | 2
|  | Send key words/phrases to QueryList function | [7 empty] | Average Daily Sprint Points Completed | 1 | 6 | 0.71429 | 1
|  | Testing | [9 empty] | 7 | 0 | 0
Test Word_Extractor function
Sprint Log 5 - Create a playlist
| User Story | Tasks
| As a user I want to be able to download my news related playlist to listen offline | SCRUM | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Start Date | 2019-11-19 | Day of the Sprint | Target | Actual
|  | Sprint Chart | [7 empty] | Sprint End Date | 2019-11-26 | 0 | 5 | #DIV/0!
|  | Pair Programming Logs | [7 empty] | Sprint Length (Days) | 7 | 1 | 4.2857 | #DIV/0!
|  | Meeting Logs | [7 empty] | Sprint Points | 5 | 2 | 3.5714 | #DIV/0!
|  | Artefact | [7 empty] | Expected Average Daily Sprint Points | 0.71429 | 3 | 2.8571 | #DIV/0!
[12 empty] | 4 | 2.1429
[10 empty] | Completion Time | 0 | 5 | 1.4286
[10 empty] | Average Daily Sprint Points Completed | #DIV/0! | 6 | 0.71429
|  | Testing | [9 empty] | 7 | 0
Sprint Log 6 - Allow music to be played
| User Story | Tasks
| As a user I want to be able to download my news related playlist to listen offline | SCRUM | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Start Date |  | Day of the Sprint | Target | Actual
|  | Sprint Chart | [7 empty] | Sprint End Date |  | 0 | #DIV/0! | #DIV/0!
|  | Pair Programming Logs | [7 empty] | Sprint Length (Days) | 0 | 1 | #DIV/0! | #DIV/0!
|  | Meeting Logs | [7 empty] | Sprint Points | 5 | 2 | #DIV/0! | #DIV/0!
|  | Artefact | [7 empty] | Expected Average Daily Sprint Points | #DIV/0! | 3 | #DIV/0! | #DIV/0!
[12 empty] | 4 | #DIV/0!
[10 empty] | Completion Time | 0 | 5 | #DIV/0!
[10 empty] | Average Daily Sprint Points Completed | #DIV/0! | 6 | #DIV/0!
|  | Testing | [9 empty] | 7 | #DIV/0!